## Introduction
Instructions:
1. The objective of the project deliverable document is to specify the mandatory work products based on the nature and size of the work and help them to comply to OPAL Processes.
2. Compliance to CMMI Level 3 shall be maintained by mapping the customer processes to all the specified work products against the applicable work classification. 1. V2Soft specific work products need to be used, or the customer specified alternative can be used. 2. Applicable metrics and metrics reporting will need to be followed
3. All the Review and Approval records for which no template identifier exists, projects can use the emails or local templates as an evidence.
4. Work is classified as (i) Large (if effort is >= 2000 person hours) - Large projects include large services and support projects. The Project involves multiple groups and requires a structured systems engineering approach to develop, integrate, deploy and manage a system product applications (ii) Medium ( if effort is between 720 person hours and <= 2000 Person hours) - New Development includes work that leads to the creation of a new solution. Enhancement includes significant new requirements, but does not alter the overall makeup of an existing solution. This may entail adding, changing, or deleting function of the existing solution. Enhancements will usually cause an impact to the business, organization or architecture, and may require significant cost, effort, and time to complete. (iii) Small Work Effort ( if effort is < 720 person hours) - Small work effort includes minor enhancement involving upto 500 person hours of effort.
Document Revision History
Date | Version | Author | Remarks
2015-10-15 | 1.0 | Venkatesh Murali | Initial draft
2015-11-05 | 1.1 | Venkatesh Murali | inclusion of Maintenance project
2016-02-02 | 1.2 | Murali V | Changes for exclusion of few documents
2016-04-06 | 1.3 | Mugilan / Sham / Murali V | Included the Testing Projects Tab, Added Project Access Control matrix, OPD Desktop proc , CM Audit report and Test Summary report
2018-06-27 | 1.3 | Sambrama | No-Change, Reviewed
V2Soft
Confidentiality Level: Internal

## Maintenance
Maintenance work effort including (Production/Enhancements support projects)
Note: | All documents need to be created in the templates provided All documents need to be saved in the format: <Process Area>_<Document_Name>_<Project Name>_Version. Ex: VAL_STP_EmployMe_V1.0.doc Questions/Comments: CMMI@V2Soft.com
Project Name
PM/POC
Team
QA
CMMI-Process Area | Document Name | Team Responsible | Remarks
REQM-Non tech | Proposal/Contract document Y/N | Proposal Team
| SOW/PO existing values Y/N | Proposal Team | work authorization for the full year
IPM | Project Tailoring Checklist | PM
PP | Initiation Checklist | Project Team
| New Project Kick-off Form | PM
| Project Management Plan (PMP) | Project Team
| Effort and Size estimation document | PM | Assumptions and dependencies, need evidence for the effort
| Effort and Schedule Sign-off from Management | PM
| Project_Access_Control_Matrix | PM
REQM | Product Traceability Matrix (PRTM) | Project Team | Optional : if new requirements are added as part of Enhancements, Propagates across all Pas for Enhancement projects
| Lessons Learned | Project Team
| Meeting_Minutes | Project team | all project meetings
| Analysis Document | Project team | Optional For Enhancements projects/ updates to existing specification document
| Analysis Sign Off from Client/Customer | Project team | Optional related to item 26
PMC
| Project Closure Report | PM - At end of project
| past performance document | PM, Project team | Performance document must be sent to the proposal team (FedSales@v2soft.com) after 3 weeks of project start
| Project Monitoring Report for every Month | PM | Measurements/Metrics
| Monthly Status Report (MSR) | PM- Monthly | To be submitted every month
CM | Component Baseline Register | Project team | Only if source code access from V2Soft environment
| Configuration Baseline Register | Project team | Only if source code access from V2Soft environment
| CR Status Accounting Sheet | Project team | Only if source code access from V2Soft environment
| CM Release Notes | Project team
| Request for Change | Project team
| CM_CONFIGURATION_AUDIT_REPORT | Project team | Audit report frequency as defined in the CMP (15 days or Monthly)
VAL | Unit Test Case | Project Team | Only if source code access from V2Soft environment
| System Test Case | QA | Only if source code access from V2Soft environment
| System Test Plan | QA | Only if source code access from V2Soft environment
| Corrective_Action_Report | Project Team | Only if source code access from V2Soft environment
| System Test bug report | Project team | Only if source code access from V2Soft environment
| System test lead signoff on the Release | PM | Only if source code access from V2Soft environment
VER | Peer review reports for all Work products | Project Team
| Corrective Action Report for all work products | Project team
| Test Plan Review checklist | Project team
| Test Case Review checklist | Project team
| Code review checklist | Project team
DAR | Decision Analysis and Resolution Report | Project Team | Optional : This PA is involved in All process areas when decisions to be made
MA |  | Project team | Measurements are collected in all PA, Monthly
V2Soft
Confidentiality Level: Internal

## Small
Small work effort( if effort is < 720 person Hours)
Note: | All documents need to be created in the templates provided All documents need to be saved in the format: <Process Area>_<Document_Name>_<Project Name>_Version. Ex: PP_BRD_EmployMe_V1.2.doc Questions/Comments: CMMI@V2Soft.com
Project Name
PM/POC
Team
QA
CMMI-Process Area | Document Name | Team Responsible | Remarks
REQM-Non tech | Proposal/Contract document Y/N | Proposal Team
| SOW/PO existing values Y/N | Proposal Team | work authorization
IPM | Project Tailoring Checklist | PM
pp | New Project Kick-off Form | PM
| Project Management Plan (PMP) - Small | Project Team | PMP includes the following: Risk, CMP, CM Audits, Communication management etc. WBS in MPP. Effort and Schedule Sign-off from Management
| Effort and Size estimation document | PM | Assumptions and dependencies
| Effort and Schedule Sign-off from Management | PM
`
COM/Infrastructure team | Material Request Form | Project Team | Request must be sent to the infrastructure team
| Resource/Personnel Request Form | Project Team and HR
| Infrastructure Access Request Form | Project Team | Request must be sent to the infrastructure team
REQM | Product Traceability Matrix (PRTM) | Project Team | Propagates across all PA's
| Lessons Learned | Project Team | Part of Small PMP
| Meeting_Minutes | Project team
| BRD Document | Project team | in the form of V2Soft template or client provided document within there template. Should cover both Functional and Non functional requirements
| BRD Sign Off Document from Client/Customer | Project team
PMC
| Project Closure Report | PM - At end of project
| past performance document | PM, Project team | Performance document must be sent to the proposal team (FedSales@v2soft.com) after 3 weeks of project start
| Weekly Status Report (WSR) | PM- Weekly (New)
CM | Component Baseline Register | Project team
| Configuration Baseline Register | Project team
| CR Status Accounting Sheet | Project team
| CM Release Notes | Project team
| Request for Change | Project team
TS | HLD | Project team | LLD is optional , so HLD can be used to add as much information as required
PI | N/A | N/A
VAL | Unit Test Case | Project Team
| System Test Case | QA
| System Test Plan | QA
| Corrective_Action_Report | Project Team
| System Test bug report | Project team
| System test lead signoff on the Release | PM
VER | Peer review reports for all Work products | Project Team
| Corrective Action Report for all work products | Project team
| BRD checklist | Project team
| Test Plan Review checklist | Project team
| Test Case Review checklist | Project team
| Code review checklist | Project team
| HLD Review checklist | Project team
DAR | Decision Analysis and Resolution Report | Project Team | This PA is involved in All process areas when decisions to be made
MA |  | Project team | Measurements are collected in all PA, Monthly
V2Soft
Confidentiality Level: Internal

## Medium
Medium New Development & Enhancement ( if effort is > 720 person hours and <= 2000 Person hours)
Note: | All documents need to be created in the templates provided All documents need to be saved in the format: <Process Area>_<Document_Name>_<Project Name>_Version. Ex: PP_BRD_EmployMe_V1.2.doc Questions/Comments: CMMI@V2Soft.com
Project Name
PM/POC
Team
QA
CMMI-Process Area | Document Name | Team Responsible | Remarks
REQM-Non tech | Proposal/Contract document Y/N | Proposal Team
| SOW/PO existing values Y/N | Proposal Team
| Feasibility Matrix | Proposal Team
| Technical Feasibility Report | Proposal Team
IPM | Project Tailoring Checklist | PM
PP | Initiation Checklist | Project Team
| New Project Kick-off Form | PM
| Kickoff Meeting agenda | Project Team
| Kickoff Meeting Checklist | Project Team
| Project Management Plan (PMP) | Project Team
| Effort and Size estimation document | PM | Assumptions and dependencies
| Risk Management Matrix | Project Team
| Effort and Schedule Sign-off from Management | PM
| Milestone Chart | PM
| WBS in MPP | PM
| Project_Access_Control_Matrix | PM
COM/Infrastructure team | Material Request Form | Project Team | Request must be sent to the infrastructure team
| Resource/Personnel Request Form | Project Team and HR
| Infrastructure Access Request Form | Project Team | Request must be sent to the infrastructure team
| CMMI_OPD_Project_ IT_Desktop_Document | PM | list the H/w and S/w and other requirements
REQM | Product Traceability Matrix (PRTM) | Project Team | Propagates across all Pas
| Lessons Learned | Project Team | Part of PMP/KR
RD | Requirements Elicitation Questionnaire | Project team
| SRS Document | Project team
| Meeting_Minutes | Project team
| BRD Document | Project team | Should include Use cases/Stories also
| BRD Sign Off Document from Client/Customer | Project team
PMC | Progress Review Report | PM- Monthly | Add section of milestone accomplishment
| Project Closure Report | PM - At end of project | PP_PROJECT_Sign-off_customer
| past performance document | PM, Project team | Performance document must be sent to the proposal team (FedSales@v2soft.com) after 3 weeks of project start
| Project Monitoring Report for every Month | PM | Metrics to be submitted to MA
| Weekly Status Report (WSR) | PM- Weekly (New)
CM | Component Baseline Register | Project team | Data Management Plan: All the records such as action log, metrics analysis document, other non deliverable data can also be recorded here
| Configuration Baseline Register | Project team | Master list of Documents: All the project related plans and reference documents
| Configuration Management Plan (CMP) | Project team | CI items such as requirement spec, design doc, code, test specification , CM Audits etc.
| CR Status Accounting Sheet | Project team
| CM Release Notes | Project team
| Request for Change | Project team
| CM_CONFIGURATION_AUDIT_REPORT | Project team | Audit report frequency as defined in the CMP (15 days or Monthly)
TS | LLD | Project team | Optional to be included in HLD
| HLD | Project team
| DAR for TS | Project team | Optional if applicable
PI | Integration Readiness Review Checklist | Project team
| Integration Test Plan | Project team
| Integration Test Case | Project team
VAL | Unit Bug report | Project Team
| Unit Test Case | Project Team
| Unit Test Plan | Project team
| System Test Case | QA
| System Test Plan | QA
| Corrective_Action_Report | Project Team
| System Test bug report | Project team
| System test lead signoff on the Release | PM
| Test Summary Report | PM
VER | Peer review reports for all Work products | Project Team
| Corrective Action Report for all work products | Project team
| BRD checklist | Project team
| Test Plan Review checklist | Project team
| Test Case Review checklist | Project team
| Code review checklist | Project team
| SRS Review checklist | Project team
| HLD Review checklist | Project team
| LLD Review checklist | Project team
DAR | Decision Analysis and Resolution Report | Project Team | This PA is involved in All process areas when decisions to be made
MA |  | Project team | Measurements are collected in all PA, Monthly
V2Soft
Confidentiality Level: Internal

## Large
Large ( if effort is >= 2000 Person hours)
Note: | All documents need to be created in the templates provided All documents need to be saved in the format: <Process Area>_<Document_Name>_<Project Name>_Version. Ex: PP_BRD_EmployMe_V1.2.doc Questions/Comments: CMMI@V2Soft.com
Project Name
PM/POC
Team
QA
CMMI-Process Area | Document Name | Team Responsible | Remarks
REQM-Non tech | Proposal/Contract document Y/N | Proposal Team
| SOW/PO existing values Y/N | Proposal Team | work authorization
| Feasibility Matrix | Proposal Team
| Technical Feasibility Report | Proposal Team
IPM | Project Tailoring Checklist | PM
PP | Initiation Checklist | Project Team
| New Project Kick-off Form | PM
| Kickoff Meeting agenda | Project Team
| Kickoff Meeting Checklist | Project Team
| Project Management Plan (PMP) | Project Team
| Effort and Size estimation document | PM | Assumptions and dependencies
| Risk Identification Checklist | Project Team
| Risk Management Matrix | Project Team
| Project Document Tracking Record | Project Team
| Effort and Schedule Sign-off from Management | PM
| Milestone Chart | PM
| WBS in MPP | PM
| Project_Access_Control_Matrix | PM
COM/Infrastructure team | Material Request Form | Project Team | Request must be sent to the infrastructure team
| Resource/Personnel Request Form | Project Team and HR
| Infrastructure Access Request Form | Project Team | Request must be sent to the infrastructure team
| CMMI_OPD_Project_ IT_Desktop_Document | PM | list the H/w and S/w and other requirements
REQM | Product Traceability Matrix (PRTM) | Project Team | Propagates across all PAs
| Lessons Learned | Project Team
| Team Charter | Project Team
RD | Requirements Elicitation Questionnaire | Project team
| SRS Document | Project team
| Use Case Document | Project team
| Meeting_Minutes | Project team
| Prototype | Project team
| BRD Document | Project team
| BRD Sign Off Document from Client/Customer | Project team
PMC | Progress Review Report | PM- Monthly
| Project Closure Report | PM - At end of project | PP_PROJECT_Sign-off_customer
| Past performance document | PM, Project team | Performance document must be sent to the proposal team (FedSales@v2soft.com) after 3 weeks of project start
| Project Milestone Review Meeting/Report | PM- End of Milestone
| CAR | PM
| Project Monitoring Report for every Month | PM
| Project Status Report (PSR) | PM - Monthly
| Weekly Status Report (WSR) | PM- Weekly (New)
CM | Component Baseline Register | Project team | Data Management Plan: All the records such as action log, metrics analysis document, other non deliverable data can also be recorded here
| Configuration Baseline Register | Project team | Master list of Documents: All the project related plans and reference documents
| Configuration Management Plan (CMP) | Project team | CI items such as requirement spec, design doc, code, test specification , CM Audits etc.
| CR Status Accounting Sheet | Project team
| CM Release Notes | Project team
| Request for Change | Project team
| CM_CONFIGURATION_AUDIT_REPORT | Project team | Audit report frequency as defined in the CMP (15 days or Monthly)
TS | LLD | Project team
| HLD | Project team
| Installation Manual | Project team
| DAR for TS | Project team
| User Manual | Project team
PI | Integration Readiness Review Checklist | Project team
| Delivery Checklist | Project team
| Integration Test Plan | Project team
| Integration Test Case | Project team
VAL | Unit Bug report | Project Team
| Unit Test Case | Project Team
| Unit Test Plan | Project team
| System Test Case | QA
| System Test Plan | QA
| Corrective_Action_Report | Project Team
| System Test bug report | Project team
| System test lead signoff on the Release | PM
| Test Summary Report | PM
VER | Peer review reports for all Work products | Project Team
| Corrective Action Report for all work products | Project team
| BRD checklist | Project team
| Test Plan Review checklist | Project team
| Test Case Review checklist | Project team
| Code review checklist | Project team
| SRS Review checklist | Project team
| Design Review checklist | Project team
| HLD Review checklist | Project team
| LLD Review checklist | Project team
DAR | Decision Analysis and Resolution Report | Project Team | This PA is involved in All process areas when decisions to be made
MA |  | Project team | Measurements are collected in all PA, Monthly
V2Soft
Confidentiality Level: Internal

## Testing Projects
Testing Project Deliverables
Note: | All documents need to be created in the templates provided All documents need to be saved in the format: <Process Area>_<Document_Name>_<Project Name>_Version. Ex: PP_BRD_EmployMe_V1.2.doc Questions/Comments: CMMI@V2Soft.com
Project Name
PM/POC
Team
CMMI-Process Area | Document Name | Team Responsible | Remarks
REQM-Non tech | Proposal/Contract document Y/N | Proposal Team
| SOW/PO existing values Y/N | Proposal Team | work authorization
| Feasibility Matrix | Proposal Team | Not Applicable
| Technical Feasibility Report | Proposal Team | Not Applicable
IPM | Project Tailoring Checklist | PM
PP | Initiation Checklist | Project Team
| New Project Kick-off Form | PM
Project Access Control Matrix
| Kickoff Meeting agenda | Project Team
| Project Management Plan (PMP) - Small | Project Team
| Effort and Size estimation document | PM | Assumptions and dependencies
| Risk Management Matrix | Project Team
| Project Document Tracking Record | Project Team
| Effort and Schedule Sign-off from Management | PM
| WBS in Xls | PM
| Project_Access_Control_Matrix | PM
COM/Infrastructure team | Material Request Form | Project Team | Request must be sent to the infrastructure team
| Resource/Personnel Request Form | Project Team and HR
OPD - Project Infrastructure and Desktop Document
| Infrastructure Access Request Form | Project Team | Request must be sent to the infrastructure team
REQM | Product Traceability Matrix (PRTM) | Project Team | Propagates across all PAs
| Lessons Learned | Project Team
| Team Charter | Project Team
RD | SRS Document | Project team | SRS Document will be provided by the Client. This is a Read-Only activity
| BRD Document | Project team | This is a Read-Only activity
| BRD Sign Off Document from Client/Customer | Project team | Testing Team to sign off the understanding of BRD Documents before starting test design
PMC | Progress Review Report | PM- Monthly | NA
| Project Closure Report | PM - At end of project
| Past performance document | PM, Project team | Performance document must be sent to the proposal team (FedSales@v2soft.com) after 3 weeks of project start
| Project Monitoring Report for every Month | PM
| Monthly Status Report (MSR) | PM - Monthly
CM | Component Baseline Register | Project team | Data Management Plan: All the records such as action log, metrics analysis document, other non deliverable data can also be recorded here
| Configuration Baseline Register | Project team | Master list of Documents: All the project related plans and reference documents
| Configuration Management Plan (CMP) | Project team | CI items such as requirement spec, design doc, code, test specification , CM Audits etc. Implement existing CM Plan and for IV and V, testing team will use our own CM Plan
| CR Status Accounting Sheet | Project team
| CM Release Notes | Project team | Receive Release notes from Client. (Client/dev release notes)
| Request for Change | Project team | Testing team to use the Org template for any CRs coming up
| CM_CONFIGURATION_AUDIT_REPORT | Project team | Audit report frequency as defined in the CMP (15 days or Monthly)
VAL | System Test Case | Project team | This includes for all types of testing example: Performance, Security, Database…
| System Test Plan | Project team | Tools to be mentioned. This includes for all types of testing example: Performance, Security, Database… Val Test Data Protection Policy
| Corrective_Action_Report | Project Team
| System Test bug report | Project team
| System test lead signoff on the Release | PM
Test Summary Report
VER | Peer review reports for all Work products | Project Team
| Corrective Action Report for all work products | Project team
| BRD checklist | Project team
| Code Review |  | As per the testing activities, review template will change
| HLD review checklist |  | Script reviews
| Test Plan Review checklist | Project team
| Test Case Review checklist | Project team
| SRS Review checklist | Project team
DAR | Decision Analysis and Resolution Report | Project Team | This PA is involved in All process areas when decisions to be made
MA | Test Metrics | Project team | Measurements are collected in all PA, Monthly
TS | HLD
V2Soft
Confidentiality Level: Internal